1-Month Code Completion + Thesis Completion Plan

This includes:

- Fully finishing the hybrid algorithm code

- Running experiments

- Collecting results

- Writing the thesis

- Preparing for submission

WEEK 1 — FINISH THE CORE CODE (A + MR-Q + HYBRID)*

Goal: Codebase complete and bug-free enough to run all experiments.

✅ DAY 1–2: Clean up environment + simulation code

- Finalize 20×20 grid environment

- Implement obstacle generation (static + dynamic)

- Fix rendering (Pygame or Matplotlib)

- Standardize coordinate system (row/col vs x/y)

✅ DAY 3–4: Finalize A*

You should already have this, but finish:

- Priority queue

- Manhattan heuristic

- Path reconstruction

- Collision checks

- Validate against multiple maps

Expected output: A* returns an optimal static path every time.

✅ DAY 5–6: Finalize MR-Q-Learning module

Implement:

- Q-table structure

- State encoding

- Reward function

- Exploration policy

- Update rule

- Max episodes + time limit

- Logging for: rewards, updates, convergence

IMPORTANT:
Make sure it handles:

- Moving obstacles

- Step penalty

- Proximity penalty

- Goal reward

- Dead-end punishment

✅ DAY 7: Implement Hybrid Controller

This is where people usually get stuck. Do this:

Hybrid logic (simple version):

If next A* node is free:

follow A* step

Else:

trigger MR-Q fallback (local)

after obstacle cleared → return to nearest A* waypoint

Need to implement:

- Detect A* path blockage in real time

- Switch to MR-Q local navigation

- Recover back to A* path

- If stuck → replan using A* again

WEEK 2 — DEBUGGING + EXPERIMENT AUTOMATION

Goal: Everything runs without crashing and logs data automatically.

✅ DAY 8–9: Debug hybrid system

Test:

- A* blocked

- MR-Q takes over

- Local detour success

- Return to A* path

Fix issues like:

- Infinite loops

- Moving obstacle path overwriting

- Q-table size explosion

- "Agent keeps spinning" issue

✅ DAY 10–11: Add experiment runner

Write a script:

- Runs multiple maps automatically

- Saves logs to CSV

- Stores path coordinates

- Saves total reward

- Saves success/fail

✅ DAY 12–13: Visualize paths

Write utility functions:

- Draw grid

- Show A* path (blue)

- Show RL path (green)

- Show hybrid path (red)

- Save images to /results folder

✅ DAY 14: Validate all components

Test all:

- A* flies perfectly in static

- Q-learning adapts in dynamic

- Hybrid = best of both worlds

WEEK 3 — RUN ALL EXPERIMENTS + ANALYZE RESULTS

Goal: Get all the data your thesis needs.

Experiments to run:

1️⃣ Static obstacles
2️⃣ High-density obstacles
3️⃣ Slow-moving obstacles
4️⃣ Fast-moving obstacles
5️⃣ Blocked path requiring full replan
6️⃣ Energy-aware battery model tests

Metrics to compute:

- Path length

- Success rate

- Collisions

- Time to goal

- Reward curves

- Battery consumption

- Path deviation from global optimum

This week deliverables:

- CSV logs

- Plots (Matplotlib)

- Screenshots of paths

- Reward convergence graphs

- A* vs RL vs Hybrid comparison tables

WEEK 4 — FINAL THESIS WRITING + PACKAGING

Goal: Deliver a complete thesis + full code.

Chapter writing tasks:

✔ Rewrite Methodology
Add pseudocode for:

- A*

- MR-Q-learning

- Hybrid switching logic

✔ Finish Experiments Chapter
Insert:

- Graphs

- Tables

- Comparison analysis

✔ Add limitations & future work
Easy section, just list:

- Heavy RL training time

- Simulation not 3D

- No wind/noise model

Code preparation:

- Clean folder structure

- Add README.md

- Add run instructions

- Add requirements.txt

- Add comments + docstrings

Final deliverables:

- Complete Python project

- All figures exported (PNG)

- Final PDF thesis formatted

Realistic Weekly Output Summary

| Week | Focus | Outcome |
| --- | --- | --- |
| 1 | Build all the code | Working A*, MR-Q, Hybrid |
| 2 | Debug + automate | Stable system + logging |
| 3 | Experiments | All graphs/tables/data |
| 4 | Thesis polish | Final submission |